## Sheet1
Gantt Chart showing SDLC Schedule for the project JOB SEARCHING WEBSITE
Created by Simran Misra on 28 September 2020
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 1 | 2020-07-17 | 2020-07-23
Problem Definition | [10 empty] | Week 2 | 2020-07-24 | 2020-07-30 | bar: Week 1
Feasibility Study | [10 empty] | Week 3 | 2020-07-31 | 2020-08-05 | bar: Week 1 to Week 2
Requirement Analysis | [10 empty] | Week 4 | 2020-08-06 | 2020-08-13 | bar: Week 2 to Created by Simran Misra on 28 September 2020 Week 3
SDLC Model used | [10 empty] | Week 5 | 2020-08-14 | 2020-08-20 | bar: Week 2
Functionalities | [10 empty] | Week 6 | 2020-08-21 | 2020-08-27 | bar: Created by Simran Misra on 28 September 2020 Week 3
Design | [10 empty] | Week 7 | 2020-08-28 | 2020-09-03 | bar: Created by Simran Misra on 28 September 2020 Week 4 to Created by Simran Misra on 28 September 2020 Week 7
DFD Level 0 | [10 empty] | Week 8 | 2020-09-04 | 2020-09-10 | bar: Created by Simran Misra on 28 September 2020 Week 4
DFD Level 1 | [10 empty] | Week 9 | 2020-09-11 | 2020-09-17 | bar: Created by Simran Misra on 28 September 2020 Week 5
DFD Level 2 | [10 empty] | Week 10 | 2020-09-18 | 2020-09-24 | bar: Created by Simran Misra on 28 September 2020 Week 6 to Created by Simran Misra on 28 September 2020 Week 7
Approx. Size Estimation | bar: Created by Simran Misra on 28 September 2020 Week 8
Implementation | bar: Created by Simran Misra on 28 September 2020 Week 7 to Created by Simran Misra on 28 September 2020 Week 10